## Test Case Tracker
Module | Module Name | Original Module No. | Planned Dates | Date Made | Module Type | Test Area | Test Case | What Is Being Tested | Pass Criteria | Why This Test Needs To Happen | Why It Passes / Evidence Expected | Test Type | Priority | Status | Evidence Location | Owner / Reviewer | Last Run Date | Notes
M0 | Project Foundation | Original M0 | 20-26 May 2026 | 2026-05-23 | Project | Foundation | M0-TC01 Repository structure baseline | Required root folders, module/app segregation, docs, contracts, tests, config, and infrastructure locations. | All expected folders exist and obsolete mixed architecture paths are either removed or documented as history only. | The rest of the project depends on a clean spec-driven structure. | The folder inventory and architecture baseline show the active implementation surfaces. | Automated + evidence | Required | Planned
M0 | Project Foundation | Original M0 | 20-26 May 2026 | 2026-05-23 | Project | Foundation | M0-TC02 Spec hygiene and module boundaries | Module specs use current architecture terms and do not point future work to obsolete folders. | Spec tests pass with no legacy/current-boundary contradictions. | Specs drive development; ambiguity creates rework between chats/modules. | Architecture hardening contract tests pass and inventories identify updated files. | Automated + evidence | Required | Planned
M0 | Project Foundation | Original M0 | 20-26 May 2026 | 2026-05-23 | Project | Config | M0-TC03 Central configuration registry | Central runtime, path, and logging registries exist and are referenced by specs/runtime. | config/stats.runtime.json, stats.paths.json, and stats.logging.json exist and are validated by tests. | Cloud/container deployment changes root paths and env values; hardcoding would break portability. | Tests confirm config files and references are present. | Automated + evidence | Required | Planned
M0 | Project Foundation | Original M0 | 20-26 May 2026 | 2026-05-23 | Project | Git workflow | M0-TC04 GitHub branch and evidence workflow | Branch naming, PR review, no Codex commit prefix rule, and evidence locations. | Feature branch exists, commits are intentional, evidence is stored under approved results/docs locations. | Production-like workflow needs traceability and review gates. | Git status/PR review artifacts and evidence indexes show the workflow. | Automated + evidence | Required | Planned
M1 | Identity Access Module | Original M1 | 20-26 May 2026 | 2026-05-23 | Standalone reusable module | Authentication | M1-TC01 Login success | Valid active user can log in and receive an access token/session. | Known test admin/user logs in successfully through UI and/or API. | All protected Stats workflows require identity first. | Container/UI evidence shows authenticated workspace access. | Automated + evidence | Required | Planned
M1 | Identity Access Module | Original M1 | 20-26 May 2026 | 2026-05-23 | Standalone reusable module | Authentication | M1-TC02 Invalid login rejection | Incorrect password, unknown user, or inactive user is rejected. | API/UI returns clear failure without token or workspace access. | Protects private financial documents and admin features. | Automated tests assert failed responses and no authenticated state. | Automated + evidence | Required | Planned
M1 | Identity Access Module | Original M1 | 20-26 May 2026 | 2026-05-23 | Standalone reusable module | Authorization | M1-TC03 Role-based access | Admin can access user management; non-admin cannot perform admin actions. | Admin-only actions reject non-admin tokens. | The app processes sensitive data and needs clear privilege boundaries. | Role tests pass and UI hides/blocks unauthorized operations. | Automated + evidence | Required | Planned
M1 | Identity Access Module | Original M1 | 20-26 May 2026 | 2026-05-23 | Standalone reusable module | Password setup | M1-TC04 First-login password change | Temporary-password user is forced to set a new password before normal access. | User cannot proceed until password setup succeeds. | Bootstrap accounts should not keep temporary passwords. | Evidence screenshot shows password reset flow and successful workspace access. | Automated + evidence | Required | Planned
M2 | Stats Web Shell | Original M1 / Frontend split | 20-26 May 2026 | 2026-05-24 | Stats product layer | Web shell | M2-TC01 Shell health and landing routes | Stats Web /health, /, /Login, /Upload, and navigation render from the app entry point. | Pages return expected status and render expected workspace elements. | The .NET shell is the user-facing entry point for all modules. | Browser evidence shows routes loaded at http://127.0.0.1:8080. | Automated + evidence | Required | Planned
M2 | Stats Web Shell | Original M1 / Frontend split | 20-26 May 2026 | 2026-05-24 | Stats product layer | Proxy | M2-TC02 Same-origin API proxy | Browser calls use Stats Web relative /api/v1/* paths instead of direct module ports. | Frontend can call APIs through Stats Web; no browser-facing module base URLs are required. | Container/cloud deployments should expose one stable web entry point. | Upload flow and proxy tests show requests routed through Stats Web. | Automated + evidence | Required | Planned
M2 | Stats Web Shell | Original M1 / Frontend split | 20-26 May 2026 | 2026-05-24 | Stats product layer | Security | M2-TC03 CORS and correlation behavior | Configured CORS origins and request correlation headers. | Allowed origins work, wildcard is not used, invalid correlation IDs are normalized. | Browser security and logs must be predictable in production. | Unit/integration tests verify CORS preflight and correlation handling. | Automated + evidence | Required | Planned
M2 | Stats Web Shell | Original M1 / Frontend split | 20-26 May 2026 | 2026-05-24 | Stats product layer | Configuration | M2-TC04 Local orchestration disabled by default | In-process local service orchestration is off unless explicitly enabled for development. | Container runtime does not start duplicate module processes from Stats Web. | Avoids fragile duplicate orchestration in production/container mode. | Config tests confirm Enabled=false and container entrypoint owns module startup. | Automated + evidence | Required | Planned
M3 | File Validation Module | Original M2 | 27 May-2 June 2026 | 2026-05-25 | Standalone reusable module | Validation | M3-TC01 Valid file acceptance | Supported PDF/image fixtures are accepted with file metadata and validation result. | Accepted files return valid status, size, extension, MIME/signature, and hash metadata. | Every later module depends on rejecting bad input early. | API tests and upload evidence show valid fixtures passing validation. | Automated + evidence | Required | Planned
M3 | File Validation Module | Original M2 | 27 May-2 June 2026 | 2026-05-25 | Standalone reusable module | Validation | M3-TC02 Invalid file rejection | Unsupported extension, MIME mismatch, oversized, missing file, and suspicious signature are rejected. | Each invalid case returns clear findings and does not proceed to ingestion. | Prevents unsafe or unusable files entering the pipeline. | Negative tests pass with explicit rejection reasons. | Automated + evidence | Required | Planned
M3 | File Validation Module | Original M2 | 27 May-2 June 2026 | 2026-05-25 | Standalone reusable module | Traceability | M3-TC03 Hash and metadata consistency | SHA/hash, filename, size, and validation findings are stable. | Repeated validation of same fixture produces consistent metadata. | Deduplication and evidence reporting need stable file identity. | Test output shows consistent hash/metadata for fixtures. | Automated + evidence | Required | Planned
M4 | File Ingestion Module | Original M2 | 27 May-2 June 2026 | 2026-05-26 | Standalone reusable module | Ingestion | M4-TC01 Validated file ingestion | A validated file creates an ingestion record/job and stores source context. | Ingestion returns accepted status, ingestion ID, storage reference, and timestamps. | The system needs a durable handoff from validation to parsing. | Cross-module test shows validation result feeds ingestion successfully. | Automated + evidence | Required | Planned
M4 | File Ingestion Module | Original M2 | 27 May-2 June 2026 | 2026-05-26 | Standalone reusable module | Ingestion | M4-TC02 Rejected validation cannot ingest | Files that fail validation are not accepted by ingestion. | Ingestion returns a controlled rejection or refuses missing validation proof. | Prevents bypassing the validation module. | Negative tests prove failed validation does not create accepted ingestion. | Automated + evidence | Required | Planned
M4 | File Ingestion Module | Original M2 | 27 May-2 June 2026 | 2026-05-26 | Standalone reusable module | Reliability | M4-TC03 Duplicate or repeated ingestion behavior | Repeated file submission is logged consistently and duplicate behavior is clear. | Duplicate submissions are identified or stored according to configured policy. | Real document workflows often resubmit the same file. | Evidence shows duplicate handling status and traceable ingestion IDs. | Automated + evidence | Required | Planned
M5 | OCR Extraction Module | Original M3 | 3-9 June 2026 | Not yet made | Standalone reusable module | OCR/Text | M5-TC01 Text extraction from PDF and image fixtures | PDF direct text path and image/scanned OCR path with metadata. | Parser returns text length, method/strategy, timing, and quality findings. | Financial documents arrive as scans, photos, and PDFs. | Container evidence shows Tesseract available and usable OCR output. | Automated + evidence | Required | Planned
M5 | OCR Extraction Module | Original M3 | 3-9 June 2026 | Not yet made | Standalone reusable module | OCR/Text | M5-TC02 Poor image handling | Low quality, rotated, faded, or hard-to-read images return warnings instead of silent success. | Result includes findings for low confidence, short text, or unsupported quality. | The user already found a real receipt image that OCR struggled to read. | Tests show warning/fallback behavior for weak OCR samples. | Automated + evidence | Required | Planned
M5 | OCR Extraction Module | Original M3 | 3-9 June 2026 | Not yet made | Standalone reusable module | Privacy | M5-TC03 Redacted evidence output | Evidence does not expose raw financial identifiers or full OCR text. | Screenshots/summaries redact sensitive values while preserving quality signals. | Capstone evidence should prove behavior without leaking private data. | Evidence index and JSON summaries omit raw extracted text and identifiers. | Automated + evidence | Required | Planned
M6 | Document Classification Module | Original M4 | 3-9 June 2026 | Not yet made | Standalone reusable module | Classification | M6-TC01 Known document classification | Extracted text is classified as bank statement, receipt, invoice, utility bill, or unknown. | Known fixture types return expected class above confidence threshold. | Downstream parsing/extraction rules depend on document type. | Classification tests compare expected type/confidence to fixture labels. | Automated + evidence | Required | Future
M6 | Document Classification Module | Original M4 | 3-9 June 2026 | Not yet made | Standalone reusable module | Classification | M6-TC02 Unknown/ambiguous handling | Ambiguous documents return unknown or low-confidence findings. | System does not overclaim a document type when evidence is weak. | Wrong classification can create wrong transactions. | Tests assert controlled unknown/low-confidence results. | Automated + evidence | Required | Future
M7 | Transaction Extraction Module | Original M5 | 3-9 June 2026 | Not yet made | Standalone reusable module | Extraction | M7-TC01 Transaction candidate extraction | Dates, descriptions, merchants/billers, amounts, direction, and categories where available. | Known transaction-like text returns candidate records and summary counts. | This is the core business value: turning document text into structured financial data. | M7 tests and container curl evidence show transaction candidates. | Automated + evidence | Required | Planned
M7 | Transaction Extraction Module | Original M5 | 3-9 June 2026 | Not yet made | Standalone reusable module | Extraction | M7-TC02 Extraction from M5 outputs | M7 accepts parse output generated by M5, not only isolated synthetic text. | M5 parse payload can be converted into M7 request and processed successfully. | Module integration catches mismatches between contracts. | Container evidence runs M7 using M5-derived payloads. | Automated + evidence | Required | Planned
M7 | Transaction Extraction Module | Original M5 | 3-9 June 2026 | Not yet made | Standalone reusable module | Quality | M7-TC03 Low confidence/finding behavior | Incomplete or noisy text returns findings and lower confidence rather than false precision. | Missing fields are flagged; confidence and finding codes are present. | Financial data needs explainable uncertainty. | Tests assert findings for incomplete records. | Automated + evidence | Required | Planned
M8 | Data Validation Module | Original M6 | 10-16 June 2026 | Not yet made | Standalone reusable module | Validation | M8-TC01 Normalize and validate transaction records | M7 transaction candidates are normalized and checked for required fields. | Valid records pass with normalized amount/date/direction fields. | Prepares data for persistence and dashboard reporting. | M8 unit tests show accepted normalized records. | Automated + evidence | Required | Planned
M8 | Data Validation Module | Original M6 | 10-16 June 2026 | Not yet made | Standalone reusable module | Validation | M8-TC02 Missing/invalid field warnings | Missing dates, invalid amounts, missing direction, and unsupported currency produce findings. | Invalid records are flagged with clear codes. | Bad financial records should not silently enter reporting. | Negative validation tests assert warning/error codes. | Automated + evidence | Required | Planned
M8 | Data Validation Module | Original M6 | 10-16 June 2026 | Not yet made | Standalone reusable module | Validation | M8-TC03 Duplicate detection within request | Duplicate-like records are detected according to configured tolerance. | Duplicate findings appear when amount/date/description match policy. | Reduces double counting in summaries. | Unit tests cover duplicate match tolerance. | Automated + evidence | Required | Planned
M9 | Stats Data and Persistence | Original M7 | 10-16 June 2026 | Not yet made | Stats product layer | Persistence | M9-TC01 Save workflow outputs | Documents, extracted text metadata, transactions, validation results, and processing logs persist. | Data remains available after service restart. | The app must retain results for review, dashboard, and reporting. | Persistence tests restart runtime and retrieve stored records. | Automated + evidence | Required | Future
M9 | Stats Data and Persistence | Original M7 | 10-16 June 2026 | Not yet made | Stats product layer | Database | M9-TC02 Migration and config-driven DB connection | Database schema migrations run against configured PostgreSQL-compatible DB. | Migrations succeed using centralized DB settings; no hardcoded connection strings. | Cloud migration requires DB settings to be environment-driven. | Migration logs and tests confirm configured DB use. | Automated + evidence | Required | Future
M9 | Stats Data and Persistence | Original M7 | 10-16 June 2026 | Not yet made | Stats product layer | Retrieval | M9-TC03 Retrieve documents and transactions | APIs retrieve stored document and transaction records with filters. | Records created by workflow can be queried after restart. | Dashboard and reporting depend on retrieval APIs. | API tests verify retrieval results match stored workflow output. | Automated + evidence | Required | Future
M10 | Stats Workflow Integration | Original integration activity | 17-23 June 2026 | Not yet made | Stats product layer | Integration | M10-TC01 End-to-end upload workflow | Upload runs validation, ingestion, OCR/parsing, extraction, validation, and persistence through contracts. | One representative fixture completes the full pipeline and returns coherent status. | Integration proves standalone modules work as a Stats product. | E2E test/evidence shows module handoffs through container. | Automated + evidence | Required | Future
M10 | Stats Workflow Integration | Original integration activity | 17-23 June 2026 | Not yet made | Stats product layer | Integration | M10-TC02 Error handoff and partial failure | Failure in one module returns clear status without corrupting later module state. | Pipeline stops or degrades according to contract and logs the failure. | Production workflows need diagnosable failures. | Tests simulate module failure and assert clear response/logs. | Automated + evidence | Required | Future
M11 | Stats Dashboard and Reporting | Original M8 | 17-23 June 2026 | Not yet made | Stats product layer | Dashboard | M11-TC01 Dashboard displays persisted results | Dashboard shows uploaded documents, transaction table, summaries, categories, and warnings. | UI displays data from backend APIs only. | Users need to inspect processed financial data visually. | Browser E2E evidence shows dashboard populated from stored records. | Automated + evidence | Required | Future
M11 | Stats Dashboard and Reporting | Original M8 | 17-23 June 2026 | Not yet made | Stats product layer | Dashboard | M11-TC02 Empty/error states | Dashboard handles no data, loading, and failed API calls gracefully. | UI shows useful states without broken layout or hidden errors. | Operational tools must remain understandable under partial data. | Playwright/browser evidence captures empty and error states. | Automated + evidence | Required | Future
M12 | Email Ingestion Module | Original M9 | Stretch / Week 5-6 | Not yet made | Standalone reusable module | Email ingestion | M12-TC01 Safe attachment retrieval | Test mailbox/mock ingestion retrieves approved attachments only. | Allowed attachment is collected and submitted to validation; unauthorized source is ignored. | Email ingestion expands intake channels and increases security risk. | Mock/test mailbox evidence shows controlled ingestion. | Automated + evidence | Required | Future
M12 | Email Ingestion Module | Original M9 | Stretch / Week 5-6 | Not yet made | Standalone reusable module | Email ingestion | M12-TC02 Deduplication and logging | Repeated email attachment is deduplicated and logged. | Duplicate is identified and not double processed. | Email attachments are commonly resent/forwarded. | Tests assert duplicate detection and processing log entries. | Automated + evidence | Required | Future
M13 | Containerization | Original M10 | 24-30 June 2026 | Not yet made | Infrastructure | Container | M13-TC01 Container stack starts | Docker Compose starts Stats Web, module APIs, DB, and Tesseract in container runtime. | stats-runtime and stats-db are healthy; module health endpoints respond. | Container runtime is the bridge to cloud deployment. | Docker compose ps/health evidence shows all services running. | Automated + evidence | Required | Planned
M13 | Containerization | Original M10 | 24-30 June 2026 | Not yet made | Infrastructure | Container | M13-TC02 Containerized browser workflow | Visible Edge workflow uses Docker-published Stats Web URL. | Screenshots show http://127.0.0.1:8080 with address bar and app workflow. | Evidence must prove the user-facing flow is not host-started services. | Architecture hardening workflow screenshots and index prove container route. | Automated + evidence | Required | Planned
M13 | Containerization | Original M10 | 24-30 June 2026 | Not yet made | Infrastructure | Config/logging | M13-TC03 Central config/logging inside container | Container exposes and consumes central runtime/path/logging env vars and files. | Terminal evidence shows config files present and logging format/destination configured. | Cloud deployment needs centrally maintained config/logging. | Container proof screenshot shows env vars, files, health, and logs. | Automated + evidence | Required | Planned
M14 | Cloud Readiness | Original M11 | 24-30 June 2026 | Not yet made | Infrastructure | Cloud readiness | M14-TC01 Azure deployment configuration | Azure target settings, secrets, storage, DB, logging, and monitoring are supplied by environment/managed services. | No local-only hardcoded values are required for cloud deployment. | Cloud migration changes roots, secrets, and service endpoints. | Deployment dry-run/checklist verifies config surfaces. | Automated + evidence | Required | Future
M14 | Cloud Readiness | Original M11 | 24-30 June 2026 | Not yet made | Infrastructure | Cloud readiness | M14-TC02 Managed secret handling | Secrets move to managed provider and are not committed or printed. | App starts with managed secret references and logs do not expose secrets. | Security/privacy is central for financial document processing. | Cloud-readiness tests/checklist verify secret sources and redaction. | Automated + evidence | Required | Future
M15 | Evaluation Evidence | Original M12 | 24-30 June 2026 | Not yet made | Project evidence | Evaluation | M15-TC01 Accuracy/completeness evaluation | Synthetic and anonymized real-document sets measure extraction accuracy and completeness. | Report includes success/failure rate, processing time, and field accuracy. | Capstone final report needs measurable evidence, not just screenshots. | Evaluation workbook/report summarizes metrics and sample outcomes. | Automated + evidence | Required | Future
M15 | Evaluation Evidence | Original M12 | 24-30 June 2026 | Not yet made | Project evidence | Evaluation | M15-TC02 Usability and evidence package | Evidence package includes screenshots, logs, test results, and usability notes. | Final evidence is organized, privacy-safe, and report-ready. | Assessment needs traceable proof of what was built and tested. | Evidence index maps tests to screenshots/results and WIP/final report sections. | Automated + evidence | Required | Future

## Module Summary
Module | Module Name | Module Type | Planned Dates | Date Made | Test Case Count | Required Count | Future Count
M0 | Project Foundation | Project | 20-26 May 2026 | 2026-05-23 | 4 | 4 | 0
M1 | Identity Access Module | Standalone reusable module | 20-26 May 2026 | 2026-05-23 | 4 | 4 | 0
M2 | Stats Web Shell | Stats product layer | 20-26 May 2026 | 2026-05-24 | 4 | 4 | 0
M3 | File Validation Module | Standalone reusable module | 27 May-2 June 2026 | 2026-05-25 | 3 | 3 | 0
M4 | File Ingestion Module | Standalone reusable module | 27 May-2 June 2026 | 2026-05-26 | 3 | 3 | 0
M5 | OCR Extraction Module | Standalone reusable module | 3-9 June 2026 | Not yet made | 3 | 3 | 0
M6 | Document Classification Module | Standalone reusable module | 3-9 June 2026 | Not yet made | 2 | 2 | 2
M7 | Transaction Extraction Module | Standalone reusable module | 3-9 June 2026 | Not yet made | 3 | 3 | 0
M8 | Data Validation Module | Standalone reusable module | 10-16 June 2026 | Not yet made | 3 | 3 | 0
M9 | Stats Data and Persistence | Stats product layer | 10-16 June 2026 | Not yet made | 3 | 3 | 3
M10 | Stats Workflow Integration | Stats product layer | 17-23 June 2026 | Not yet made | 2 | 2 | 2
M11 | Stats Dashboard and Reporting | Stats product layer | 17-23 June 2026 | Not yet made | 2 | 2 | 2
M12 | Email Ingestion Module | Standalone reusable module | Stretch / Week 5-6 | Not yet made | 2 | 2 | 2
M13 | Containerization | Infrastructure | 24-30 June 2026 | Not yet made | 3 | 3 | 0
M14 | Cloud Readiness | Infrastructure | 24-30 June 2026 | Not yet made | 2 | 2 | 2
M15 | Evaluation Evidence | Project evidence | 24-30 June 2026 | Not yet made | 2 | 2 | 2

## Legend
Field | Meaning
What Is Being Tested | The behavior, contract, or workflow under test.
Pass Criteria | Observable result required to call the test passed.
Why This Test Needs To Happen | Risk or business/engineering reason for the test.
Why It Passes / Evidence Expected | What proof should be produced when the test passes.
Status | Planned means it is part of the tracker now; Future means the module is not yet built or is scheduled later.
Evidence Location | Fill this with paths under tests/results, test-results, or docs/evidence when executed.

## Notes
Stats Module Test Case Tracker
Source roadmap | C:\000_Capstone\docs\Stats_Module_Roadmap.xlsx
Created for | Spec-driven module-by-module testing and evidence tracking
Container policy | From M13 onward, official regression/evidence should run through the containerized runtime unless explicitly documented otherwise.
Configuration policy | Tests should verify configurable paths, ports, logging, database settings, and environment values are centrally maintained.
Privacy policy | Evidence should avoid raw OCR text, passwords, bearer tokens, card numbers, and account numbers.